## All
Site # | Site Name | Date Established | Monitored by | Grade (s) | County | GPS Coordinates (NAVD 88 decimal degrees) | Agencies with Oversight | Site Description | Treatment Type and Date | Observations (include date) | Flooding in Spring 2017
1 | Alameda | Apr 1997 | Bosque School | 6 | Bernalillo | 35.18805064, -106.6469194 | MRGCD, ABQ Open Space | mature cottonwood overstory with dense New Mexico olive understory; one of the most native (90%) sections of the bosque throughout ALbuquerque; oldest BEMP site | Jun 2004 cleared; Sept 05 - Apr 06 drinking water diversion dam (DWDD) construction on east side; Mar 2007 site mulched near east well and east of main horse trail; Feb 2012 work being done on dam - diverted or stopped water; Jul 2012 whole dam up, working downstream of dam
2 | Rio Grande Nature Center | Jun 1997 | Wilson MS | 6 | Bernalillo | 35.12675286, -106.6884322 | MRGCD, ABQ Open Space | numerous thin cottonwoods with some Russian olive understory; lots of clover; very open site | Jun 2004 understory cleaning prompted by a nearby bosque fire; Jan 2005 - Apr 2006 DWDD construction
3 | Los Lunas | Oct 1997 | Los Lunas High School | 9-12 | Valencia | 34.81236936, -106.7144580 | MRGCD | large, older cottonwood overstory with mostly native understory of willow, New Mexico olive, wild currant, some Russian olive and saltcedar; yerba mansa covers much of the ground; experiencing more and more large branches falling; seep flood through a trough that runs through the center of the site | 1997 flood, May 2009 seep flood; other seep floods? |  | Site flooded in May 2017
4 | Belen | Feb 1998 | Rio Grande Elementary School | 2 | Valencia | 34.6484315, -106.7377022 | MRGCD, Valencia SWCD | 15 year-old cottonwoods, willows and Russian olives; experiences overbank flooding with high surface flow | 2004? overbank flood; other years?; 2007 low ground fire; Apr-May 2008 flood; Mar 2010 east part of site flooded |  | Site flooded in May 2017
5 | Santa Ana | Jul 1999 | Bernalillio MS | 7 | Bernalillo | 35.34284°, -106.5458 | Santa Ana Pueblo, MRGCD | cottonwood gallery forest with little to no understory | when? cleared of exotics by Sandia Pueblo’s Department of Natural Resources; Aug 1999 some flooding from upland runoff from adjacent site
6 | Savannah | Mar 2000 | Bosque School | 6 | Bernalillo | 35.14285294, -106.6819814 | ABQ Open Space | grasses and forbs with pockets of overstory cottonwood stretching above an understory of Russian olive, saltcedar and older woody-stemmed plants | mowed annual by private land owner prior to the City purchasing the property in 2003; Jun 2003 A line burned; Jan 2005 - Apr 2006 DWDD construction
7 | Lemitar | Sep 2002 | Parkview ES | 3 | Socorro | 34.16703188, -106.8899486 | MRGCD | north of Socorro Nature Area; only site outside the levee; most xeric site; open landscape with a sparse cover of grasses, forbs, broom dalea, sand sage, and four-wing saltbush; handful of stunted cottonwoods and clumps of saltcedar | none
8 | Hispanic Cultural Center (HCC) | fall 2001 started, finished Apr 2002 | School on Wheels | 10 - 12 | Bernalillo | 35.06881267, -106.6580575 | MRGCD, ABQ Open Space | cottonwood-dominated bosque with light understory of elm, Russian olive and Gooding's willows; tall wheatgrass getting denser each year | when? cleared of woody litter and invasive tree species by City of Albuquerque Open Space and the extensive removal of jetty jack lines; May 2004 exotics removed - lots of heavy machinery in site; Jan 2005 - Apr 2006 DWDD construction |  | western edge flooded, not fully on site
9 | Ohkay Owingeh | Mar 2002 | OOCS | 4-5 | Rio Arriba | 36.0618, -106.0761 | Pueblo of Ohkay Owingeh | located by an extensive constructed wetland; periodically flooded by rising wetland water and a correspondingly rising adjacent water table; few large cottonwoods, few Russian olive resprouts; heavily vegetated by mostly native shrubs, vines, forbs and grasses | 2001 cleared of invasive vegetation; Sep 2002 flood; Jun 2003 burned; Aug 2003 flooded; 04-09 flooded almost every summer; Apr 2010 burned; May-Jun 2010 flooded; May-Jul 2011 flooded; May-Jun 2012 flooded; starting Aug 2012 cows allowed to roam in site. As of December 2015, site no longer monitored | Sep 2012 about 6 cottonwood root sprouts about 1 m high; most cottonowods are dying from last fire
10 | Diverson | Nov 2002 | Bosque School | 6 | Bernalillo | 35.191958, -106.6441893 | MRGCD, ABQ Open Space | sparse, young pole-planted cottonwoods in this site with some elm; very open and sandy site; DWDD located directly north of site; wells have automated groundwater recording devices as part of a collaboration between the US Army Corps of Engineers Urban Flood Demonstration and the University of New Mexico. | 2003 cleared?; Sept 05 - Apr 2006 DWDD construction on east side; Feb 2012 work being done on dam - diverted water; Jul 2012 whole dam up and working downstream of it | Jan-Feb 2006 all wells dry; Jan 2011 lots of beaver activity H-I lines; Mar 2011 beaver activity through whole site; Aug 2011 more beaver activity through site
11 | Calabacillas | Jan 2003 | Volcano Vista HS | 15 | Bernalillo | 35.19056822, -106.6491626 | MRGCD, ABQ Open Space | mature cottonwood-dominated bosque with little to no understory | 2003 cleared? Sept 05 - Apr 06 DWDD construction on east side; Sep 2011 dead and down wood mulched
12 | Minnow | Dec 2002 | Bandelier Elementary | 5 | Bernalillo | 35.19315094, -106.646915 | MRGCD, ABQ Open Space | cottonwood-dominated bosque with a couple Gooding's willows, otherwise little understory; wells have automated groundwater recording devices as part of a collaboration between the US Army Corps of Engineers Urban Flood Demonstration and the University of New Mexico. | early 2003 rain gauges installed; Mar 2004 veg plots, litterfall bins and pitfalls installed; Jan-Apr 2005 DWDD construction on west side; Sep 2011 dead and down wood mulched; Jan 2012 cottonwood poles planted close to river; Feb 2012 work being done on dam - diverted water; Jul 2012 whole dam up and working downstream of it
13 | Harrison | Spring 2003 | Highland HS | 9 - 12 | Bernalillo | 35.01505603, -106.6736953 | MRGCD, ABQ Open Space | located in a sand bar; covered with young cottonwoods, lots of willows, some seepwillow and some Russian olives; floods when river is high | side channel created; May 2005 flood buried E well; May 2007 flood; 2009 flood, Apr-May 2010 flood; Mar 2012 wetland scallops created in site; Aug 2012 flash flood (3,000 cfs); July 26, 2013 3600 cfs from rain: entire site flooded and had 1 in of mud 4 days later (pit trap 20, open rain gauge and G tub not flooded) | have seen lots of beaver and porcupine activity since side channel was created | Site flooded in April and May 2017
14 | Sevilleta | Spring 2003 | Cottonwood Valley Charter School | 4 | Socorro | 34.25834233, -106.8831845 | Sevilleta National Wildlife Refuge, MRGCD | southern boundary of Sevilleta National Wildlife Refuge upstream of San Acacia Diversion Dam; dense woody vegetation of mostly Russian olive and saltcedar mixed with cottonwoods and a patchy understory of coyote willow; most cottonwoods are saplings; site has high groundwater salinity and soils contain heavy clay; occasional swards and small meadows dominated by saltgrass occur among trees | installed Oct 2003; Jun 2004 pitfalls installed; Oct 2009 or 2008? mud flood (6 inches of water, 4 inches of mud) | Sept. 19, 2009 site flooded (several inches) due to rain/river stage according to Steven Yanoff; 2010, 2011 and 2012 seeing many cottonwoods rot at stem base and die; Aug 2012 lots of green cottonwood leaves on ground
15 | Valencia Cleared | Spring 2003 | Belen HS | 9-12 | Valencia | 34.64863444, -106.7391728 | MRGCD, Valencia SWCD | few cottonwoods, Gooding's willows, Russian olives with large patches of wolfberry and ground cover of yerba masa | May 2003 Valencia SWCD cleared and chipped; 2008 re-cleared; road through eastern edge of site Oct 2012 |  | Site had seep flooding in May 2017
16 | Valencia Forest | Spring 2003 | Belen Family Schools | 3-6 | Valencia | 34.64716225, -106.738482 | MRGCD, Valencia SWCD | was uncleared and dominated by cottonwood, Russian olive, saltcedar with a saltgrass meadow at the south end of the site; after fire and clearings, now almost entirely covered by kochia and tumbleweed with small patches of yerba mansa and saltgrass | Feb 2007 site burned; May 2008 MRGCD cleared and piled dead cottonwoods and much saltcedar and Russian olive regrowth; Oct 2008 more piles of wood created, bulldozing, S well destroyed; Apr 2009 cleared and chopped wood; Mar 2010 more clearing; Mar 31, 2010 masticated large wood piles
17 | Montaño | May 2004 | Bosque School | 6 | Bernalillo | 35.14528819, -106.6803699 | ABQ Open Space | contains a few cottonwoods; northern section covered in kochia and tumbleweed; middle of site thick with tree of heaven | Jun 2003 burned; Jul 2004 post-fire restoration work under contract to Ciudad SWCD including: downing and chipping standing dead snags, removal and chemical herbicide treatment of emerging exotics, and planting natives; Jan 2005 - Apr 2006 DWDD construction; Jan 2012 site mowed; Sep/Oct 2012 northern half of site mowed; Dec 2012 northern half of site has trampled plants (though not mowed)
18 | Reynolds Cleared | Spring 2004 | Infinity High School | 9-12 | Valencia | 34.65966431, -106.7421328 | MRGCD, Valencia SWCD | fairly open site with young cottonwood canopy of pole plantings, with kochia and tumbleweed and also New Mexico olive planted by river | Feb/Mar 2004 cleared by Valencia SWCD, cottonwood pole plants installed; Feb 2012 Russian olive and saltcedar cut, treated and dispersed | Aug-Sep 2012 tons of kochia and tumbleweed after it was dying back the past five years | seep flooding
19 | Reynolds Forest | Spring 2004 | School of Dreams Academy | 9-12 | Valencia | 34.66054583, -106.7429525 | MRGCD, Valencia SWCD | cottonwood overstory with a saltcedar and Russian olive understory; yerba mansa patches in northern section of site, wild currant interspersed; site continues to experience cottonwood dieback leading to the high woody debris load (prior to clearing in Feb 2012) | Aug 2004 veg plots, litterfall bins and pitfalls installed; Feb 2012 site cleared entirely except for live cottonwoods - everything mulched to the ground | Aug-Sep 2012 lots of kochia and tumbleweed | Site flooded in May 2017
20 | Route 66 | Sep 2004 | Jefferson MS | 6-8 | Bernalillo | 35.1006408, -106.6914783 | MRGCD, ABQ Open Space | natural seep or trough in the center of the site that is thickly vegetated with willows with some elm and Russian olive; cottonwoods line the trough; east and west sides of the trough cleared by Albuquerque Open Space every few years and are vegetated by kochia and tumbleweed | Dec 2004 veg plots, litterfall bins and pitfall traps installed; Jan 2005 - Apr 2006 DWDD construction; spring 2008 cleared northern half of site, including willows; Oct 2008 recleared entire site except trough; Apr 2010 site flooded in trough; May 2011 site flooded in trough |  | Site flooded in April and May 2017
21 | Badger | Dec 2004 wells; Jul 2006 rest of site | RRCA | 6 | Bernalillo | 35.19556856, -106.6416219 | MRGCD, ABQ Open Space | cottonwood-dominated bosque with elm sub-canopy; most wells have automated groundwater recording device as part of a collaboration between the US Army Corps of Engineers Urban Flood Demonstration and the University of New Mexico. | Sept 05 - Apr 06 DWDD construction on east side; Sep 2011 dead and down wood mulched; Feb 2012 work being done on dam - diverted water; Jul 2012 whole dam up and working downstream of it
22 | Bobcat | Dec 2004 wells; Aug 2006 rest of site | La Cueva | 10 - 12 | Bernalillo | 35.19705633, -106.6439494 | MRGCD, ABQ Open Space | cottonwood-dominated bosque with a couple Gooding's willows; C well has automated groundwater recording device as part of a collaboration between the US Army Corps of Engineers Urban Flood Demonstration and the University of New Mexico. | Jan-Apr 2005 DWDD construction on west side; Sep 2011 dead and down wood mulched; Feb 2012 work being done on dam - diverted water; Jul 2012 whole dam up and working downstream of it
23 | BioPark | Feb 2007 | Albuquerque Institute of Math and Science (AIMS) | 7 | Bernalillo | 35.06688861, -106.7202778 | MRGCD, ABQ Open Space | medium sized cottonwoods over elm and Russian olive sub-canopy; wetland to the west of site, pond to the northwest of site | Dec 2007 cleared of exotic understory (elm, Russian olive); Jul 2010 small fire by E well and NE section of site; Nov 2010 cleared of exotic understory; Oct 2011 dead and down wood mulched; Nov 2012 east edge of site cleared of discarded asphalt and cement (large machinery in site) |  | Site flooded in May 2017
24 | Santo Domingo (Kewa) | Jan 2008 | Santo Domingo Natural Resources Department | . | Sandoval | 35.50989, -106.3896 | Santo Domingo Tribe Natural Resources Dept. | sparse cottonwood overstory with scattered juniper, New Mexico olive and willow understory; lots of grasses; horse activity at site | prior to site installation cleared as part of a CFRP grant for the pueblo
25 | Crawford | Sep 2008 | UNM interns | . | Valencia | 34.6375111, -106.7434661 | MRGCD, Valencia SWCD | strongly hydrologically connected, with seep floods occuring at higher flows; northern section: cottonwoods in low-lying areas with saltcedar and kochia in higher areas, lots of cocklebur; southern section: yerba mansa, rushes and sedges, kochia; vegetation almost equally native and exotic; Collaborative Forestry Research Program (CFRP) site | Feb 2007 burned; Jun 2007 MRGCD chopped and cleared resprouting exotic trees and larger dead cottonwoods; Jan-Feb 2009 MRGCD cleared site again; Feb 2009 Interstate Stream Commission lowered terrace and adjacent banks creating a backwater area when river flows reach 2500 cfs; May 2009 flood; May 2010 flood |  | Overbank flooding at site in April, but wells not flooded for monthly monitoring; overbank flooding in May 2017
26 | Mesilla | Jun 2011 | John Paul Taylor | elementary | Doña Ana | 32.248328, -106.821014 | Mesilla Valley Bosque State Park, MRGCD | primarily kochia with sparse wood chip piles and some native forbs | Apr 2011 site totally cleared of saltcedar with bulldozers, wood stacked in large piles to burn at a later date; Oct 2012 cleared of kochia | summer 2012 lots of kochia at site
27 | Bosque Farms | Feb 2012 | The International School | 7 | Valencia | 34.848851, -106.714722 | MRGCD, Valencia SWCD | first site immediately south of Albuquerque; cottonwood-dominated bosque with some native grasses and willows on the east side, closer to the river | Exotic removal occurred a few years prior to site establishment |  | Site flooded in April and May 2017
28 | Valle de Oro | January 2014 | South Valley Academy | 9-12 | Bernalillo | 34.97895, 106.6801 | USFWS | site was installed ouside of levee system on a fallow farm field. No trees or shrubs, primarily various forb ground cover | no treatments to date - site will eventually be transformed into a wetland area fed by stormwater runnoff
29 | Albuquerque Overbank Project (AOP) | established in 1998, BEMP took over in March 2014 | La Academia de Esperanza HS | 9-12 | Bernalillo | 35.04546°, -106.6657° | MRGCD, ABQ Open Space | mature cottonwoods along east side of site, west side was lowered and experiences overbank flooding during high flows, lots of young cottonwoods and coyote willow, | 1998: Bank lowering, and exotic removal and creation of side channel; overbank flooding: 1998, 1999, 2001, 2015 (possibly 2013 and 2005), 2003- removal of Russian olive |  | Site flooded in April and May 2017
30 | State Land Office | June 2014 | The International School | 3-4 | Bernalillo | 34.96785, 106.6856 | State Land Office | moderately dense mature cottonwood overstory with two large trenches dug through the sited for stormwater runoff drainage to the river; some trenches with permentant standing water supporting coyote willow stands. Much of site outside of ditches covered with tumbleweed and kochia | Prior to site installation; site cleared of exotics, trenches dug throughout bosuqe, and grass seeding along eastern side of site |  | Site flooded in April and May 2017 - seep flood rather than overbank flood
31 | San Jose | Dec 2015 | NACA | 12 | Bernalillo | 35.012375, 106.6727833 |  | site installed in USACE constructed willow swale. High flow channel runs through the center of the swale and innundates around 2,500 cfs. | Restoration construction of willow swale, high flow channel, and nearby bank terracing began in 2012 and completed in 2014 | Dec 2015 - high flow channel innunated | Site flooded in April and May 2017
32 | Sandia Pueblo | Feb 2016 | Mountian View ES | 3 | Bernalillo | 35.255°, -106.5907° |  | high intensity burn site with many dead standing and down cottonwoods (few living), revegetated with seepwillow and native grasses; some sunflowers, silverleaf nightshade, and occassional Russian olive. | USACE began bank terracing, exotic removal, and native vegetation planting in 2012 and a fire (started in Corrales) jumped the river into the restoration site and burned much of the area that same year. Regegetation efforts have

## for reports1
Site Name | Date Established | Monitored by | Grade (s) | County | GPS Coordinates (NAVD 88 decimal degrees) | Site Description
Alameda | Apr 1997 | Bosque School | 6 | Bernalillo | 35.1880506, -106.646919 | mature cottonwood overstory with dense New Mexico olive understory; one of the most native (90%) sections of the bosque throughout ALbuquerque; oldest BEMP site
Albuquerque Overbank Project | established in 1998, BEMP took over in March 2014 | La Academia de Esperanza HS | 9-12 | Bernalillo | 35.04546, -106.6657 | mature cottonwoods along east side of site, west side was lowered and experiences overbank flooding during high flows, lots of young cottonwoods and willows
Badger | Dec 2004 wells; Jul 2006 rest of site | Rio Rancho Cyber Academy | 6 | Bernalillo | 35.19556856, -106.6416219 | cottonwood-dominated bosque with elm sub-canopy; most wells have automated groundwater recording device as part of a collaboration between the US Army Corps of Engineers Urban Flood Demonstration and the University of New Mexico.
Belen | Feb 1998 | Rio Grande Elementary | 2 | Valencia | 34.6484315, -106.7377022 | 15 year-old cottonwoods, willows and Russian olives; experiences overbank flooding with high surface flow
BioPark | Feb 2007 | Albuquerque Institute of Math and Science | 7 | Bernalillo | 35.06688861, -106.7202778 | medium sized cottonwoods over elm and Russian olive sub-canopy; wetland to the west of site, pond to the northwest of site
Bobcat | Dec 2004 wells; Aug 2006 rest of site | La Cueva | 10 - 12 | Bernalillo | 35.19705633, -106.6439494 | cottonwood-dominated bosque with a couple Gooding's willows; C well has automated groundwater recording device as part of a collaboration between the US Army Corps of Engineers Urban Flood Demonstration and the University of New Mexico.
Bosque Farms | Feb 2012 | UNM interns | . | Valencia | 34.848851, -106.714722 | first site immediately south of Albuquerque; cottonwood-dominated bosque with some native grasses and willows on the east side, closer to the river
Calabacillas | Jan 2003 | Volcano Vista HS | 9-12 | Bernalillo | 35.19056822, -106.6491626 | mature cottonwood-dominated bosque with little to no understory
Crawford | Sep 2008 | UNM interns | . | Valencia | 34.6375111, -106.7434661 | strongly hydrologically connected, seep floods occuring at higher flows; northern section: cottonwoods in low-lying areas with saltcedar and kochia in higher areas, lots of cocklebur; southern section: yerba mansa, rushes and sedges, CFRP site
Diverson | Nov 2002 | Bosque School | 6 | Bernalillo | 35.191958, -106.6441893 | sparse, pole-planted cottonwoods, few elm; very open and sandy site; DWDD located directly north of site;
Harrison | Spring 2003 | Highland HS | 9 - 12 | Bernalillo | 35.01505603, -106.6736953 | located on a sand bar; covered with young cottonwoods, lots of willows, some seepwillow and some Russian olives; floods when river is high
Hispanic Cultural Center | fall 2001 started, finished Apr 2002 | School on Wheels | 10 - 12 | Bernalillo | 35.06881267, -106.6580575 | cottonwood-dominated bosque with light understory of elm, Russian olive and Gooding's willows; tall wheatgrass getting denser each year
Lemitar | Sep 2002 | Parkview ES | 3 | Socorro | 34.16703188, -106.8899486 | north of Socorro Nature Area; site outside the levee; xeric site; open landscape with a sparse cover of grasses, forbs, broom dalea, sand sage, and four-wing saltbush; handful of stunted cottonwoods and clumps of saltcedar
Los Lunas | Oct 1997 | Los Lunas High School | 9-12 | Valencia | 34.81236936, -106.7144580 | large, older cottonwood overstory with mostly native understory of willow, New Mexico olive, wild currant, some Russian olive and saltcedar; yerba mansa covers much of the ground; experiencing more and more large branches falling; seep flood through a trough that runs through the center of the site
Site Name | Date Established | Monitored by | Grade (s) | County | GPS Coordinates (NAVD 88 decimal degrees) | Site Description
Mesilla | Jun 2011 | John Paul Taylor | 5 | Doña Ana | 32.248328, -106.821014 | primarily kochia with sparse wood chip piles and some native forbs
Minnow | Dec 2002 | Bandelier Elementary | 5 | Bernalillo | 35.1931509, -106.646915 | cottonwood-dominated bosque with a couple Gooding's willows, otherwise little understory; wells have automated groundwater recording devices as part of a collaboration between the USACE Urban Flood Demonstration and UNM.
Montaño | May 2004 | Bosque School | 6 | Bernalillo | 35.14528819, -106.6803699 | contains a few cottonwoods; northern section covered in kochia and tumbleweed; middle of site thick with tree of heaven
Ohkay Owingeh | Mar 2002 | OOCS | 4-5 | Rio Arriba | 36.0618, -106.0761 | located by an extensive constructed wetland; periodically flooded by rising wetland water and a correspondingly rising adjacent water table; few large cottonwoods,history of few large fires, mostly native shrubs, vines, forbs and grasses
Reynolds Cleared | Spring 2004 | Infinity High School | 9-12 | Valencia | 34.65966431, -106.7421328 | fairly open site with young cottonwood canopy of pole plantings, with kochia and tumbleweed and also NM olive planted by river
Reynolds Forest | Spring 2004 | School of Dreams Academy | 9-12 | Valencia | 34.66054583, -106.7429525 | cottonwood overstory with a saltcedar and Russian olive understory; yerba mansa patches in northern section of site, wild currant interspersed; site continues to experience cottonwood dieback leading to the high woody debris load (prior to clearing in Feb 2012) - post 2013 clearing: kochia understory with thick woodchips from exotic clearing
Rio Grande Nature Center | Jun 1997 | Wilson MS | 6 | Bernalillo | 35.12675286, -106.6884322 | numerous thin cottonwoods with some Russian olive understory; lots of clover; very open site
Route 66 | Sep 2004 | Jefferson MS | 6-8 | Bernalillo | 35.1006408, -106.6914783 | natural seep or trough in the center of the site that is thickly vegetated with willows with some elm and Russian olive; cottonwoods line the trough; east and west sides of the trough cleared by Albuquerque Open Space every few years and are vegetated by kochia and tumbleweed
Sandia | Feb 2016 | Mountian View ES | 3 | Bernalillo | 35.255, -106.5907 | high intensity burn (2012) site with many dead standing and down cottonwoods (few living), revegetated with seepwillow and native grasses; some sunflowers, silverleaf nightshade, and occassional Russian olive.
San Jose | Dec 2015 | NACA | 12 | Bernalillo | 35.012375, -106.6727833 | site installed in USACE constructed willow swale. High flow channel runs through the center of the swale and innundates around 2,500 cfs. Mature cottonwoods on west side of site
Santa Ana | Jul 1999 | Bernalillio MS | 7 | Bernalillo | 35.34284, -106.5458 | Dying cottonwood gallery forest with understory of kochia
Santo Domingo (Kewa) | Jan 2008 | Santo Domingo Nat Res Dept | . | Sandoval | 35.50989, -106.3896 | sparse cottonwood overstory with scattered juniper, New Mexico olive and willow understory; lots of grasses; horse activity at site
Savannah | Mar 2000 | Bosque School | 6 | Bernalillo | 35.14285294, -106.6819814 | grasses and forbs with pockets of overstory cottonwood stretching above an understory of Russian olive and saltcedar
Sevilleta | Spring 2003 | Cottonwood Valley Charter School | 4 | Socorro | 34.25834233, -106.8831845 | southern boundary of Sevilleta NWR upstream of San Acacia Diversion Dam; dense woody vegetation of mostly Russian olive and saltcedar mixed with smaller cottonwoods and a patchy understory of coyote willow; site has high groundwater salinity and soils contain heavy clay; occasional saltgrass dominated swards occur among trees
Site Name | Date Established | Monitored by | Grade (s) | County | GPS Coordinates (NAVD 88 decimal degrees) | Site Description
State Land Office | June, 2014 | The International School | 3-4 | Bernalillo | 34.96785, -106.6856 | moderately dense mature cottonwood overstory with two large channels dug through site intended for stormwater runoff drainage to the river; some trenches with permentant standing water supporting coyote willow stands. Much of site outside of ditches covered with tumbleweed and kochia
Valencia Cleared | Spring 2003 | Belen HS | 9-12 | Valencia | 34.64863444, -106.7391728 | few cottonwoods, Gooding's willows, Russian olives with large patches of wolfberry and ground cover of yerba masa
Valencia Forest | Spring 2003 | Belen Family Schools | 3-6 | Valencia | 34.64716225, -106.738482 | was uncleared and dominated by cottonwood, Russian olive, saltcedar with a saltgrass meadow at the south end of the site; after fire and clearings, now almost entirely covered by kochia and tumbleweed with small patches of yerba mansa and saltgrass
Valle de Oro | January 2014 | South Valley Academy | 9-12 | Bernalillo | 34.97895, -106.6801 | site was installed ouside of levee system on a fallow farm field. No trees or shrubs, primarily various forb ground cover

## History by year
Site Name | 1997 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017
Alameda | Site installed (April) | [6 empty] | Cleared in June | Drinking water diversion dam constrcution on east side (DWDD) (September-April 2006) | Drinking water diversion dam constrcution on east side (DWDD) (September 05 -April) | Site mulched near east well and east of main horse trail (March) |  |  |  |  | Work being done on dam- diverted or stopped water (February); Whole dam up, working on dowstream of dam (July)
Albuquerque Overbank Project (AOP) |  | Site established; Bank lowering, and exotic removal and creation of side channel; Overbank flooding | Over bank flooding |  | Over bank flooding |  | Removal of Russian Olive |  | Possibly over bank flooding | [7 empty] | Possibly over bank flooding | BEMP took over (March) |  | overbank flooding in the spring | March-April: N end of site chipped, bulldozed, burned! May: flooded all the way up to the levee (>5 ,000 cfs), dry by June monitoring
Badger | [7 empty] | Wells installed (December) previously cleared | DWDD construction on east side (September - April 2006) | Rest of Site installed (July); DWDD construction on east side (September 2005 - April) |  |  |  |  | Dead and down wood mulched (September) | Work being done on dam-diverted water (February); Whole dam up and working downstream of it (July) |  |  |  |  | NM forest service cleared exotics in area and chipped. Small elms log piles left in area.
Belen |  | Site installed (February); overbank flooding in May | Overbank flooding in May, 1999 |  |  |  |  | Overbank flood in May | flooding in April & May |  | Low ground fire on west side (February) | Flood (April-May) ? | lowering along the east side of the site, at the river's edge in March; flooding in early May | East part of site flooded (March) | [6 empty] | March - overbank flooding May - overbank flooding
BioPark | [10 empty] | Site installed (February); Cleared of exotic understory (elm, Russian olive) (December) |  |  | Small fire by east well and NE section of site (July); East edge of site cleared of discarded asphalt and cement (large machinery in site) (November) | [6 empty] | May - flooding (seep?) through center trail of site (up to knee height)
Bobcat | [7 empty] | Wells installed (December) | DWDD construction on west side (January - April) | Rest of site installed (August) |  |  |  |  | Dead and down wood mulched (September) | Work being done on dam-diverted water (February); Whole dam up and working downstream of it (July)
Bosque Farms | [15 empty] | Site installed (February); Exotic removal occurred a few years prior to site establishment |  |  |  |  | March - Overbanking near W well May - Major seep and overbank flooding throughout site all the way to the levee
Calabacillas | [5 empty] | site installed (October) |  | cleared | DWDD construction on east side (September - April 2006) | DWDD construction on east side (September 2005 - April) |  |  | cleared |  | Dead and down wood mulched (September)
Crawford | [10 empty] | Burned (February); MRGCD chopped and cleared resprouting exotic trees and larger dead cottonwoods (June) | Site Installed (September) | MRGCD cleared site again (January - February); Interstate stream Commission lowered terrace and adjacent banks creating a backwater area when river flows reach 2500cfs (February); Flood (May) | Flood (May) - Litterfall tubs installed in site, first collection in October | [6 empty] | March - Major overbanking throughout site May - Major overbanking throughout site again!!
Diverson | [5 empty] | Site installed (August) | Cleared? |  | DWDD construction on east side (September - April 2006) | DWDD construction on east side (September 2005 - April); All wells dry (January-February) |  |  |  |  | Lots of beaver activity through H-I lines (January); Barver activity through whole site (March); More beaver activity through site (August) | Work being done on dam - diverted water (February); Whole dam up and working downstream of it (July) |  |  |  |  | March - Overbanking from the fish channel from B tub south past N well May - Overbanking in same spot again!
Harrison | [6 empty] | Site installed (Spring); Side channel created (No Date); Have seen lots of beaver and porcupine activity since side channel was created |  | Flood buried east well (May) |  | flood | Flood (May)? Not likely | flood (May) | Flood (April-May) |  | Wetland scallops created in site (March); Flash flood (3,000 cfs) (August) | 3600 cfs from rain: entire site flooded and had 1 in of mud 4 days later (pit trap 20, open rain gauge and G tub not flooded) (July 26) |  |  |  | March - Overbanking throughout the site! Constructed channel ~20in deep @ 3000 cfs May - major overbanking throughout site!!
Hispanic Cultural Center (HCC) |  |  |  |  | Site installation started (Fall) | Site installation finished (April); Cleared of woody litter and invasive tree species by City of Albuquerque Open Space and the extensive removal of jetty jack lines (No date) |  | Exotics removed - lots of heavy machinery in site (May) | DWDD construction (January - April 2006) | DWDD construction (January 2005 - April) | [10 empty] | May - Flooding along western side of site ~ 5m from W well
Lemitar |  |  |  | Site Installed (September)
Los Lunas | Site installed (October) | [11 empty] | Seep flood (May); Other seep floods? | [7 empty] | March - seepflooding in center swale May - MAJOR seep flooding (waist deep) throughout site
Mesilla | [14 empty] | Site installed (June); site totally cleared of saltcedar with bulldozers, wood stacked in large piles to burn at a later date (April) | Lots of kochia at site (Summer); Cleared of kochia (October)
Minnow | [5 empty] | Site installed (December) | Rain gauges installed early this year | Veg plots, litterfall bins and pitfalls installed (March) | DWDD construction on west side (January - April) | [5 empty] | Dead and down wood mulched (September) | Cottonwood poles planted close to river (January); work being done on dam - diverted water (February); whole dam up and working downstream of it (July) | cleared??
Montaño | [6 empty] | Burned (June) | Site installed (April); Post-fire restoration work under contract to Ciudad SWCD including: downing and chipping standing dead snags, removal and chemical herbicide treatment of emerging exotics, and planting natives (July) | DWDD construction (January - April 2006) | DWDD construction (January 2005 -April) | [5 empty] | Site mowed (January); Northern half of site mowed (September/October); Northern half of site has trampled plants (though not mowed) (December)
Ohkay Owingeh |  |  |  |  | Cleared of invasive vegetation | Site installed (March); Flood (September) | Burned (June); Flooded (August) | Flooded almost every summer | Flooded almost every summer | Flooded almost every summer | Flooded almost every summer | Flooded almost every summer | Flooded almost every summer | Burned (April); Flooded (May - June) | Flooded ( May - July) | Flooded (May - June); Cows allowed to roam in site (August); About 6 cottonwood root sprouts about 1 m high; most cottonowods are dying from last fire (September)
Reynolds Cleared | [7 empty] | Site Installed (April); Cleared by Valencia SWCD, cottonwood pole plants installed (February/March) | [7 empty] | Russian olive and saltcedar cut, treated and dispersed (February); Tons of kochia and tumbleweed after it was dying back the past five years (August-September) |  |  |  |  | May - seep flooding throughout eastern part of site
Reynolds Forest | [7 empty] | Site intalled (Spring); Veg plots, litterfall bins and pitfalls installed (August) | [7 empty] | Site cleared entirely except for live cottonwoods - everything mulched to the ground (February) |  |  |  |  | May - seep flooding throughout eastern part of site, waist deep through central swales
Rio Grande Nature Center | Site installed (June) | [6 empty] | Understory cleaning prompted by a nearby bosque fire (June) | DWDD construction (January-April 2006) | DWDD construction (January 2005-April)
Route 66 | [7 empty] | Site installed (December); Veg plots, litterfall bins and pitfall traps installed (December) | DWDD construction (January-April 2006); flooding | DWDD construction (January 2005-April) | flooding | Cleared northern half of site, including willows (Spring); Recleared entire site except trough (October); flooding | flooding | Site flooded in trough (April) | [6 empty] | March - seep flooding in center swale May - MAJOR seep flooding in center swale
Sandia | [15 empty] | USACE began bank terracing, exotic removal, and native vegetation planting in 2012 and a fire (started in Corrales) jumped the river into the restoration site and burned much of the area that same year. | planting & seeding (failed) | planting & seeding (failed) | planting & seeding | Site installed (February)
San Jose | [15 empty] | Restoration construction of willow swale, high flow channel, and nearby bank terracing begins |  | Completion of restoration construction of willow swale, high flow channel, and nearby bank terracing | Site installed (December); High flow channel innunated (December) |  | March and May - high flow channel and swale completely innundated from entrance to exit @ 3000 - 5700 cfs
Santa Ana |  |  | Site installed (July); Cleared of exotics by Sandia Pueblo’s Department of Natural Resources (No date) | [17 empty] | June 29th - herbicide treatment
Santo Domingo (Kewa) | [11 empty] | Site installed (January); Prior to site installation cleared of trash as part of a CFRP grant for the pueblo
Savannah |  |  |  | Site installed (March) |  |  | Mowed annual by private land owner prior to the City purchasing the property; A line burned (June) |  | DWDD construction (January-April 2006) | DWDD construction (January 2005-April)
Sevilleta | [6 empty] | Site installed (October) | Pitfalls installed (June) |  |  |  | flooded in Sept (several inches); Mud flood (6 inches of water, 4 inches of mud) (October) due to precip? Was under 2009; doublecheck |  | Seeing many cottonwoods rot at stem base and die | Seeing many cottonwoods rot at stem base and die | Seeing many cottonwoods rot at stem base and die; Lots of green cottonwood leaves on ground (August)
State Land Office | [17 empty] | June 2014 site installed; Prior to site installation (Jan/Feb. 2014) site cleared of exotics, trenches dug throughout bosuqe, and grass seeding along eastern side of site |  |  | March -Site cleared of invasives, herbacide treatment used May - seep flooding throughout channels and swales
Valencia Cleared | [6 empty] | Site installed (June); Valencia SWCD cleared and chipped (May) | seep flood west well |  |  |  | Re-cleared (exotic regrowth cut and left in piles); seep flood west well | seep flood west well | seep flood west well |  | Road through eastern edge of site (October) |  |  |  |  | seep flood
Valencia Forest | [6 empty] | Site installed (June) |  |  |  | Site burned (February) | MRGCD cleared and piled dead cottonwoods and much saltcedar and Russian olive regrowth (May); More piles of wood created, bulldozing, South well destroyed (October) | Cleared and chopped wood (April) | More clearing (March); Masticated large wood piles (March 31)
Valle de Oro | [17 empty] | Site installed (January); No treatments to date - site will eventually be transformed into a wetland area fed by stormwater runnoff | Elm trees cut down at site (summer time)

## Sheet1
mean gw correlation to river flow
Pearson Correlation Coefficient
site | R^2 | site stuff | treatment | site | broad category |  | clearing date
1 | -0.72971 | old | cleared | Ala | cleared |  | 2004-06-01
2 | -0.63119 | old, stressed | cleared | RGNC | cleared |  | 2004-06-01
3 | -0.54342 | old | seep | LL | flood
4 | -0.82633 | young | overbank | Bel | flood
5 |  | old | cleared | SA | cleared |  | always
6 | -0.73391 | mowed | mowed | Sav | mowed
7 | -0.5245 | old, outside levee | none | Lem | upland
8 | -0.83454 | old | cleared | HCC | cleared |  | 2004-05-01
9 |  | old, then burned | burn | OO | burn/flood |  | 2001
10 | -0.52684 | old | cleared | Div | cleared |  | 2003
11 | -0.73166 | old | cleared | Cal | cleared |  | 2003
12 | -0.76058 | old | cleared | Min | cleared |  | 2003
13 | -0.91021 | young | overbank | Harr | flood
14 | -0.46693 | med-old, saline | seep | Sev | flood
15 | -0.85714 | old, cleared | cleared | VC | cleared | seep flood | always
16 | -0.86615 | 2007 burn | burn | VF | burn |  | 2008-05-01
17 | -0.79075 | post-burn | mowed | Mon | mowed |  | always
18 | -0.8966 | cleared, old cottonwoods | cleared | RC | cleared |  | always
19 | -0.89133 | old, cleared in 2014?? | none | RF | cleared |  | 2012-02-01
20 | -0.84707 |  | mowed | Rt66 | cleared | willow swales | 2008-10-01
21 | -0.57448 | above dam | cleared | Bad | cleared
22 | -0.47989 | above dam | cleared | Bob | cleared
23 | -0.8172 | old | cleared | BioP | cleared |  | 2007-12-01
24 |  | old |  | SD | upland |  | always
25 | -0.9156 | young | overbank | Craw | flood
26 |  |  | mesilla | Mes | upland |  | always
27 |  |  | cleared | BF | cleared